## Flow Chart
AtMA Autotech Enginners Pvt.Ltd
Magnetic Marelli UM
Color Code
Software layout |  | program done but trail pending | Machine ID | DI | DO | AI | AI vs DI | AO | Servo | Scanner
|  | Done | 280 | 16 | 32 | 1-Load cell 1 LVDT | 23 | 0 | 2 | 1
User login Window |  | Configuration | DAQ Config |  | Daq port and line change | [7 empty] | off line done
|  | Manual | Scanner Config |  | barcode scanner port congiguration as and check the status of port is working or not working | [7 empty] | off line done
|  | Test Mode | Model Create |  | admin can be create, edit & delete from data base. | [7 empty] | offline done
|  | Report | File Save Pattern Config |  | admin can be zdefine the file save location & save method. Examaple:-STATUS_NIP_RRMMDD_HHMMSS.jpg (e.g. PASS_073A6H0K4W17_170213_003355.jpg) | [7 empty] | offline done
|  | Quality | Transducer Calibration |  | Load cell and other analog input signal configuration | [7 empty] | offline done
|  |  | Manual IO on-Off |  | check the input , output & analog signal | [7 empty] | off line & simulation status done
|  |  | General IO Config |  | General Io Config During the machine program start check the initial general config IO Status as per model wise. | [7 empty] | off line done
|  |  | User Management |  | admin can change the user id And password of operator and quality | [7 empty] | off line done
[13 empty] | */ | 0
*
Simulation Test Mode program done but online trail pending
Test Mode |  | DAQ System |  | 1 | in testing window display the graph and Image and other test data , save result data after complete the 30 or 40 part (setable data) check the standard deviation in product. | [7 empty] | only trail pending
Vision Image
|  |  |  | 2 | display cycle time |  |  | OK and NG Counter |  |  | Comulative Counter
[5 empty] | Login Name Display |  |  | Counter Reset |  |  | Home Indicator
|  |  |  | 3 | machine maintenance due date display (Date & Time) yellow sign mean due dtae near & Red Sign Machine Not Working this alarm rest by mainenance login id
|  |  |  | 4 | Vision Image Call by FTP And Data transfer with file. | [7 empty] | Program done trail pending
|  |  |  | 5 | setting data min, max and Actual Showing On test screen,pass condition background will be green &NG Condition Red
|  |  |  | 6 | In NG Condition Red T/L And Buzzer Active , it will be stop after press the reset button
|  |  |  | 7 | In NG condition M/c home after press the home button on computer softbutton
8
9
|  |  |  | 10 | when user press the reset button then all counter value will be reset other wise counter reset after shift change.
Histogram Analysis
Report | Deferct train analysis | [7 empty] | in testing window display the graph and Image and other test data , save result data after complete the 30 or 40 part (setable data) check the standard deviation in product.(1) display cycle time(2) OK and NG Counter(3)User Login name display(4) Alarm Status Display(5)Machine Working Condition Display(6)machine maintenance due date display (7)-------
Setting Window | SQL Configuration
New table Create Method
Header create
Emage Save Enable & Disable require at general config
Servo Motor | Calculation of Servo motor & setting Parameter in excel sheet report | [5 empty] | 2020-03-16 |  |  |  | AJAY KUMAR | Done
CALIBRATION | Program under Development Condition | [5 empty] | 2020-03-16 |  |  |  | AJAY YADAV | Done
Alarm History Generate | TBD
Raw data Save | All test data save in database software (SQL- express) | [5 empty] | 2020-03-22 |  |  |  | AJAY KUMAR | Off line Program done virtualy checked
Report | .csv report is done but customised report generation is under process | [5 empty] | 2020-03-26 |  |  |  | AJAY Yadav | Done

## Quality
CP & CPh
|  |  | R&R | only data save During the & R &R
Quality | SPC |  | CPV Calculation setting
| FTQ |  | FAIL/PASS
| RESET | when user press the reset button then all counter value will be reset other wise counter reset after shift change. |  |  | OK Counter
Fail Counter
Commulative Counter