## Sheet2
Sr. No | Task Name | Sub Task Name | Status of Project (MMUM) | Remarks
1 | Intialize | Paths
Notifires and Queue
Data base
Main data type control
2 | Analog Input Control | Acquire Analog input
Integrate with auto cycle
Integrate with Manual cycle
Calibrate Analog input
3 | Digital Input(AI) Control | Acquire Digital input (AI)
Integrate with auto cycle
Integrate with Manual cycle
4 | Digital Input Control | Acquire Digital input |  |  | e
Integrate with auto cycle
Integrate with Manual cycle
5 | Generate Digital Outputs | Generate Digital Outputs
Integrate with auto cycle
Integrate with Manual cycle
6 | Generate Analog Outputs | Generate Analog Outputs
Integrate with auto cycle
Integrate with Manual cycle
Calibrate Analog input
7 | Slide Servo Control | Genrate Pulses(Fixed Pulses)
Start & Stop Trigger
Integrate with auto cycle
Integrate with Manual cycle
Calibrate Servo Pulses
Genrate Pulses(Continous)
Start & Stop Trigger
Integrate with auto cycle
Integrate with Manual cycle
8 | Rolling Servo Control | Genrate Pulses(Fixed Pulses)
Start & Stop Trigger
Integrate with auto cycle
Integrate with Manual cycle
Calibrate Servo Pulses
Genrate Pulses(Continous)
Start & Stop Trigger
Integrate with auto cycle
Integrate with Manual cycle
9 | Barcode Control | Read Barcode data
Integrate with auto cycle
Integrate with Manual cycle
10 | Robot Control | Read Robot data Via Modbus TCP
Write Robot data Via Modbus TCP
Integrate with auto cycle
Integrate with Manual cycle
11 | Camera-1 Control | Trigger Camera
Get Camera result
Integrate with auto cycle
Integrate with Manual cycle
12 | Camera-1 Control | Trigger Camera
Get Camera result
Integrate with auto cycle
Integrate with Manual cycle
13 |  | Manual Mode UI
Integrate with Analog input
Integrate with Digital input (AI)
Integrate with Digital input